## Sheet1
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | USER STORIES | SCRUM TEAM ASSIGNED | USER STORY STEP DEFINITION 1 | USER STORY STEP DEFINITION 2 | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARK
1 | high | user001 | Account Management | team1 | Create account | Verify identity | Ravi | 3 days | 3 days | In progress | NA
2 | medium | user002 | Fund Transfers | team2 | Initiate transfer | Confirm transfer | Mansi | 2 days | 2 days | not started | NA
3 | high | user003 | Bill Payments | team3 | Add biller | Pay bill | Rushikesh | 1 day | 1 day | not started | NA
4 | medium | user004 | User Registration | team4 | Fill registration form | Verify email | Priya | 3 days | 4 days | In progress | NA
5 | high | user005 | Loan Management | team5 | Apply for loan | Upload documents | Yashwanth | 5 days | 4 days | not started | NA
6 | medium | user006 | Investment Services | team6 | Select investment | Confirm investment | Raushan | 4 days | 3 days | completed | NA
7 | low | user007 | Notifications | team7 | Set notification preferences | Receive notifications | Neelesh | 2 days | 2 days | not started | NA
8 | medium | user008 | Customer Support | team8 | Submit query | Get response | Shahwaz | 2 days | 2 days | pending | NA
9 | high | user009 | Admin Dashboard | team9 | View analytics | Manage users | Mriganka | 6 days | 6 days | not started | NA